## Summary
LUNA / ECLISSI DEVELOPMENT COST BREAKDOWN
Project Tapestry — Sovereign AI Infrastructure
LABOR RATE TIERS
Tier | Hourly Rate | Description | Use Case
Nonprofit/Grant | 75 | Discounted rate for mission-aligned work | Grant budgets, nonprofit partnerships
Market Rate | 150 | Standard senior architect/full-stack rate | Commercial contracts, "true cost" valuation
Premium/Consulting | 200 | Specialist rate for AI/sovereignty expertise | High-stakes consulting, expert testimony
DEVELOPMENT PHASES — TOTAL COST BY TIER
Phase | Timeline | Hours | Nonprofit ($75/hr) | Market ($150/hr) | Premium ($200/hr)
Phase 1: ROSA Demo Prototype | 2 months (Jan-Mar 2026) | 320 | 24000 | 48000 | 64000
Phase 2: MVP / Year 1 | 10 months (Mar 2026 - Jan 2027) | 1200 | 90000 | 180000 | 240000
Phase 3: Year 2 Scaling | 12 months (2027) | 1600 | 120000 | 240000 | 320000
TOTAL (All Phases) |  | 3120 | 234000 | 468000 | 624000

## Phase 1 - ROSA Demo
PHASE 1: ROSA CONFERENCE DEMO PROTOTYPE
Timeline: January - March 2026 (8 weeks)
Task Category | Description | Hours | Nonprofit | Market | Premium
Luna Core Engine | SQLite memory system, context management, basic inference pipeline | 80 | 6000 | 12000 | 16000
Eclissi Database Schema | Knowledge graph structure, clan-based access control design | 40 | 3000 | 6000 | 8000
Luna ↔ Eclissi Bridge | API layer connecting companion to cultural database | 32 | 2400 | 4800 | 6400
Luganda LLM Integration | Ganda Gemma 1B integration, Ollama setup, quantization testing | 40 | 3000 | 6000 | 8000
Demo UI/UX | Minimal viable interface for conference presentation | 48 | 3600 | 7200 | 9600
Hardware Integration | Raspberry Pi / edge device setup, offline deployment packaging | 32 | 2400 | 4800 | 6400
Testing & QA | Integration testing, edge case handling, demo rehearsal | 24 | 1800 | 3600 | 4800
Documentation | Technical docs, demo script, presentation materials | 24 | 1800 | 3600 | 4800
PHASE 1 TOTAL |  | 320 | 24000 | 48000 | 64000
NON-LABOR COSTS (Phase 1)
Item | Description | Cost
Edge Compute Device | Raspberry Pi 5 (8GB) + case + power supply | 150
Development Hardware | SSD, cables, peripherals for testing | 200
Cloud Compute (Dev) | GPU instances for model testing (2 months) | 300
Software/Services | API costs, development tools, licenses | 150
Conference Costs | Demo equipment, travel support if in-person component | 500
Non-Labor Subtotal |  | 1300

## Phase 2 - MVP Year 1
PHASE 2: MVP / YEAR 1 DEVELOPMENT
Timeline: March 2026 - January 2027 (10 months)
Task Category | Description | Hours | Nonprofit | Market | Premium
Luna Memory System V2 | Advanced memory architecture, relationship modeling, context windows | 160 | 12000 | 24000 | 32000
Eclissi Full Implementation | Complete knowledge graph, multi-tribe support, version control | 200 | 15000 | 30000 | 40000
Access Control System | Clan-based permissions, elder override, TK Labels integration | 120 | 9000 | 18000 | 24000
Multi-language Support | Beyond Luganda: framework for additional languages | 80 | 6000 | 12000 | 16000
Offline Sync Engine | Peer-to-peer sync, conflict resolution, data sovereignty | 120 | 9000 | 18000 | 24000
Mobile Application | Cross-platform (React Native or Flutter), tablet-optimized | 160 | 12000 | 24000 | 32000
Voice Interface | Speech-to-text, text-to-speech for oral tradition support | 80 | 6000 | 12000 | 16000
Cultural Content Tools | Elder recording interface, story capture, media handling | 80 | 6000 | 12000 | 16000
Admin Dashboard | Hub management, usage analytics, content moderation | 60 | 4500 | 9000 | 12000
Security Hardening | Encryption, secure enclaves, penetration testing | 60 | 4500 | 9000 | 12000
Integration Testing | Full system testing, Kinoni pilot preparation | 40 | 3000 | 6000 | 8000
Documentation & Training | User guides, facilitator training materials | 40 | 3000 | 6000 | 8000
PHASE 2 TOTAL |  | 1200 | 90000 | 180000 | 240000

## Infrastructure Tiers
KINONI ICT HUB — INFRASTRUCTURE COST PROJECTIONS
Tiered deployment options for different funding scenarios
TIER DEFINITIONS
Tier | Description | Capacity | Use Case
Minimal | Proof of concept, single location | 5-10 concurrent users | ROSA demo, pilot testing
Standard | Functional community hub | 20-30 concurrent users | Year 1 Kinoni deployment
Full | Complete implementation | 50+ concurrent users | Scaled regional hub
YEAR 1 INFRASTRUCTURE COSTS
Category | Item | Minimal | Standard | Full
Power | Solar panels + batteries | 3000 | 8000 | 15000
Power | Installation & wiring | 500 | 1500 | 3000
Power | Backup generator | 0 | 800 | 1500
Connectivity | Starlink kit | 600 | 600 | 600
Connectivity | Starlink service (12 mo) | 1440 | 1440 | 1440
Connectivity | Local mesh network | 0 | 500 | 1500
Devices | Tablets (Android) | 1000 | 4000 | 10000
Devices | Raspberry Pi units | 300 | 900 | 2000
Devices | Charging station | 200 | 500 | 1000
Devices | Protective cases/accessories | 200 | 600 | 1500
Facility | Furniture (tables, chairs) | 300 | 800 | 2000
Facility | Security (locks, safe) | 100 | 300 | 500
Facility | Signage & branding | 100 | 250 | 500
Operations | Maintenance reserve (10%) | 774 | 2019 | 4054
YEAR 1 TOTAL |  | 8514 | 22209 | 44594
ANNUAL RECURRING COSTS (Year 2+)
Category | Item | Minimal | Standard | Full
Connectivity | Starlink service (12 mo) | 1440 | 1440 | 1440
Operations | Device replacement (15%) | 150 | 550 | 1350
Operations | Maintenance & repairs | 300 | 800 | 1500
Operations | Consumables (power, etc.) | 200 | 400 | 800
ANNUAL RECURRING |  | 2090 | 3190 | 5090

## Robotics (Separate)
LUNA ROBOTICS — PHYSICAL CHASSIS (SEPARATE BUDGET)
Note: This is tracked separately from software development
Component | Description | Est. Cost | Status
Chassis/Shell | 3D printed or fabricated enclosure | 500 | Design phase
Display Module | Galaxy face display (OLED/LCD) | 150 | Sourcing
Ball-joint Base | 360° rotation mechanism | 200 | Design phase
Retractable Neck | Expressive movement system | 300 | Concept
Compute Module | Raspberry Pi 5 or Jetson Nano | 150 | Specified
Audio System | Speakers + microphone array | 100 | Sourcing
Power System | Battery + charging circuit | 150 | Design phase
Sensors | Proximity, touch, ambient light | 100 | TBD
Assembly/Fabrication | Labor for physical build | 1000 | TBD
Dust Protection | Desert-rated sealing | 200 | TBD
ROBOTICS TOTAL |  | 2850

## Total Project Cost
TOTAL PROJECT COST — ALL COMPONENTS
YEAR 1 TOTAL BY LABOR TIER (Software + Infrastructure)
Component | Nonprofit ($75/hr) | Market ($150/hr) | Premium ($200/hr)
Phase 1 Labor (ROSA Demo) | 24000 | 48000 | 64000
Phase 1 Non-Labor | 500 | 500 | 500
Phase 2 Labor (MVP) | 90000 | 180000 | 240000
Infrastructure (Standard Tier) | 22209 | 22209 | 22209
YEAR 1 TOTAL | 136709 | 250709 | 326709
QUICK REFERENCE — ROSA DEMO ONLY
Phase 1 Labor + Non-Labor: | 24500 | 48500 | 64500