## Assumptions
California Tribal Deployment — Cost Model
Team of 3 · 6 Months · Generic Template
TEAM — Monthly Rates
Ahab (Architecture / Tech Lead) | 8000 | Core team
Tarcila (Ops / Community Bridge) | 8000 | Core team — contract
Developer/Engineer (Contract) | 10000 | Adjust to market/skill level
TEAM — ALLOCATION (months active out of 6)
Ahab — months active | 6 | Full duration
Tarcila — months active | 5 | Phases 1,3,5,6 + overlap
Developer — months active | 4 | Phases 2,4 + testing
OVERHEAD — Monthly
Legal / Entity | 200 | LLC + registered agent amortized
Health Insurance | 500 | Sole proprietor marketplace
Software / Tools | 300 | Claude, domains, dev tools
Self-Employment Tax Rate | 30% | ~15.3% SE + ~15% effective income
Contingency Rate | 10% | Buffer for unknowns
TRAVEL — California (no international)
Round-Trip Mileage/Gas per Visit | 200 | LA to tribal land — adjust for distance
Per Diem (lodging + food) | 150 | Per person per day on-site
Days per Visit | 5 | Mon-Fri on-site
Number of Visits | 6 | Roughly monthly
People Traveling | 2 | Ahab + Tarcila usually
HARDWARE — Passthrough
Devices (tablets/laptops) | 2000 | They likely have some already
Networking (router/mesh) | 500
Backup/Storage Hardware | 300 | External drives, UPS
Misc | 500 | Cases, cables, adapters
CONSULTING — Outside Specialists
Tribal Data Sovereignty Legal Review | 3000 | One-time — NAGPRA/OCAP compliance
Language/Cultural Consultant (per session) | 2000 | If localization needed
Number of Cultural Consult Sessions | 3 | Phases 1 and 3

## 6-Month Model
Factor 1: What It Costs You
California Tribal · 6 Months · Team of 3
TEAM COMPENSATION
Ahab (6 months) | 48000 | Full duration
Tarcila (5 months) | 40000 | Phases 1,3,5,6
Developer/Engineer (4 months) | 40000 | Phases 2,4 + testing
Team Subtotal | 128000
OVERHEAD (6 months)
Legal + Health + Tools | 6000
TRAVEL
Mileage/Gas (all visits) | 1200
Per Diem (all visits) | 9000 | rate × days × visits × people
Travel Subtotal | 10200
HARDWARE (passthrough)
Hardware Total | 3300 | Billed at cost
OUTSIDE CONSULTANTS
Legal Review (tribal data sovereignty) | 3000
Cultural/Language Consultant | 6000
Consulting Subtotal | 9000
TOTALS
Project Subtotal (pre-tax/buffer) | 156500
Self-Employment Tax (Ahab comp only) | 14400 | Tax on your earnings, not contractors
Contingency Buffer | 15650
TOTAL COST (What It Costs You) | 186550
Factor 2: What You Charge
Margin Target | 20% | Adjust based on funder
CHARGE TO CLIENT / GRANT | 223860
Gross Margin $ | 37310
Grant Budget Breakdown
Personnel — Core Team (Ahab + Tarcila) | 88000 | 47.17%
Personnel — Contracted Developer | 40000 | 21.44%
Overhead & Administration | 6000 | 3.216%
Travel & Per Diem | 10200 | 5.468%
Equipment & Hardware | 3300 | 1.769%
Consultants & Specialists | 9000 | 4.824%
Tax & Contingency | 30050 | 16.11%
Total (pre-margin) | 186550 | 100%

## Phase Timeline
Phase Timeline — 6 Month Deployment
Phase | Duration | Ahab | Tarcila | Developer
1. Assessment & Governance Design | 3 weeks | Part-time | Full-time | —
2. Infrastructure & Hardware Setup | 2 weeks | Full-time | — | Full-time
3. Knowledge Seeding | 6 weeks | Part-time | Full-time | Part-time
4. Software Config & Testing | 4 weeks | Full-time | — | Full-time
5. Training & Capacity Building | 4 weeks | Part-time | Full-time | Part-time
6. Handoff & Sustainability | 2 weeks | Full-time | Full-time | —
Buffer / Iteration | 3 weeks | As needed | As needed | As needed
Total: ~24 weeks (6 months)

## CA Tribal Notes
California Tribal Deployment — Key Considerations
WHAT CHANGES VS. INTERNATIONAL
No solar needed — grid power available | Saves $2,500+
No international flights — driving distance | Saves $8K+ per trip
Better device availability | May reduce hardware budget
English as working language (usually) | Less localization overhead
LEGAL LANDSCAPE
Tribal sovereignty has federal legal standing | Different from international frameworks
NAGPRA compliance if cultural objects/remains data | Legal review covers this
OCAP® principles align with Luna sovereignty model | Natural fit for the pitch
Tribal IRB may be required for knowledge seeding | Build council relationship early
CA AB 52 and tribal consultation requirements | Legal review covers this
TRUST & RELATIONSHIP
History of extractive research programs | Trust is earned, not assumed
Tarcila leads community relationship | Tech follows trust, not the other way around
Start with Phase 1 as standalone engagement | Let them evaluate before committing to full deployment
GRANT LANDSCAPE
Bureau of Indian Affairs (BIA) | Tribal priority allocations
IMLS (Institute of Museum & Library Services) | Native American/Hawaiian Library Services grants
NEA / NEH | Cultural preservation and documentation
First Nations Development Institute | Capacity building grants
California tribal-specific state programs | Research current offerings